## MIVAN CHECKLIST
QUALCONN
CHECKLIST FOR ALU-FORM WORK AND CONCRETE WORKS
PROJECT: |  | GRADE OF CONCRETE:
LOCATION: |  | QUANTITY IN CUM:
FLOOR: |  | DATE OF CONCRETE:
POUR NO: |  | CONCRETE START TIME:
GRID REFERENCE: |  | CONCRETE END TIME:
DRAWING REFERENCE: |  | CONCRETE DURATION:
SL NO | DESCRIPTION OF ITEMS |  | YES | NO | NA | Remarks
GENERAL
1 | Method of statement submitted
A: | LAY OUT AND MARKING : | Date:
1 | Check for proper line and level of concrete surface.
2 | Check the marking with approved drawing.
3 | Check for diagonals and dimensions in marking
4 | Check for alignment of Kicker and dimensional features
B: | REINFORCEMENT WORK FOR WALLS/COLUMNS/SLAB : | Date:
1 | Check rebar’s positioning for startup marking and proceed accordingly.
2 | Check for the rebar work as per drawing.
3 | Check for required spacing’s, lapping, stirrup etc. in the rebar work.
4 | Check for proper cover blocks fixed before wall forms erection.
5 | Check for extra rebar for openings or cut outs and locations/level
6 | Check for proper binding of reinforcement steel.
C: | EMBEDMENTS FOR WALLS/COLUMNS/SLAB : | Date:
1 | Check for location of electrical conduits.
2 | Check for location / level of electrical boxes.
3 | Check for location/level of plumbing lines, sleeves etc. cut outs in the walls.
4 | Check for any insert plates, sleeves if any.
D: | WALL FORM WORKS: | Date:
1 | Check for Kicker line, level, alignment and dimensional accuracy
2 | Check if the working platform with safety nets are arranged as desired.
3 | Check for proper cleaning and oiling of panels before fixing.
4 | Check for required tools, tackles and accessories available with the team.
5 | Check for sufficient pins and wedges as required for the work.
6 | Check for the sequential panels being fixed as per the drawing.
7 | Check for proper form tie fixing, bracings.
8 | Check for openings such as doors, windows, beams, cornice, boxes, etc.
9 | Check for verticality and alignment of panels.
E: | SLAB FORM WORKS: | Date:
1 | Check for proper cleanliness and oiling of panels.
2 | Check for proper fixing of panels as per drawing.
3 | Check for proper levelling and alignment of panels.
4 | Check for right angle and diagonal dimensions and arresting same at site
5 | Check for proper slab panel level to allow for rebar works
F: | CHECK DURING CONCRETING Date:
1 | Check for proper grade and quantity
2 | Check for grade wise pour details and ensure grade separations
3 | Check for proper arrangement made at construction joint location for the pour
4 | Check for proper vibrations/tapping done during concreting
5 | Check if conduits, cut outs, sleeves, inserts, any embedment’s are in position
6 | Check if the level of concrete is maintained as per mark in kicker.
7 | Check for finishing level and thickness of concrete
G: | CHECK AFTER CONCRETE Date:
1 | Check for setting of concrete to permit de striking of wall panels
2 | Check for proper method followed for curing and duration
3 | Check for proper tools and procedure followed for removal of pins/wedges
4 | Check for proper removal of PVC sleeves and ties
5 | Check for collection of pins and wedges for the wall panels
6 | Check for proper removal of slab panels in orderly manner
7 | Check if the required verticals are left in position for slab panels
8 | Check for surface finish, level and line.
9 | Check for proper removal of slab panels in orderly manner
10 | Check if the required verticals are left in position for slab panels
11 | Check for surface finish, level and line.
Site / QC Incharge PMC Inchare Client Incharge